## Sheet1
Related User Story | Task Description | Initial Estimate | ACTUAL | Amount Remaining After…
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4
As a user, I need a UI to use the software | Implement UI (fxml and codebehind) | 7 |  | 27.75 | 18.5 | 9.25 | 0
As a user, I need to be able to create an expense | Implement Expense Class | 3
As a user, I need to have multiple expenses so I can create a budget | Implement a Budget Class | 2
As a user, I need to view budget statistics | Implement an Budget Statistics Class | 5
As a user, I need my budget saved | Implement persistence (File IO) | 4
As a user, I need to visualize my budget | Implement the budget as a graph | 5
As a user, I need to protect my financial data | Implement encryption | 3
As a user, I need information to update as I create or remove expenses | Implement UI binding and update the display | 5
| Prepare and make submission | 0.5
| Research Encryption and Graph libraries | 2.5
| Estimate Totals | 37 | Actual: ~9 | 27.75 | 18.5 | 9.25 | 0